## Sheet1
GREAT PAXTON PARISH PLAN
This Plan is an informal document intended to record the progress of the Parish Council, in an easy read format, insofar as regulatory respsonsibilities as well as additional projects and undertakings are deemed appropriate. The Plan should be read in conjunction with the Minutes of meetings for greater detail or clarification.
This Plan will be updated as a live document, will be an agenda item at all meetings and will be published on the Parish Council Website.
Some statutory and ongoing items will always remain on the Parish Plan whilst others will be removed once fully completed or where they have reached a natural conclusion. Those items removed will remain on record.
ITEM NUMBER | DESCRIPTION | ACTION | LEAD | RESOURCE IMPLICATION | TIMESCALE | NEXT REVIEW | STATUS | DISCUSS PROGRESS AT NEXT MEETING
1 | Action Plan Content and Relevance | Continuous review. Agenda item at all meetings. Full review at Annual Meeting. Updated version posted to website after each meeting. | Parish Council | LOW | ONGOING | 2024-05-20 |  | YES
RUNNING UPDATE: Plan adopted by Parish Council on 16/10/23
2 | Street Lighting | Ensure that all parish owned street lighting is maintained with inspections at prescribed intervals and action taken accordingly. Balfour Beatty conduct monthly inspections as part of contract. | Parish Council | HIGH | ONGOING | ONGOING |  | NO
RUNNING UPDATE:
3 | Grounds Maintenance Contract | Ensure that contract is being met to required standard. | Parish Council | MEDIUM | Contract, 3 years | 2026-01-01 |  | YES
RUNNING UPDATE: The grounds maintenance and bin emptying contracts have been split between HDC & a new Grounds Maintenance Contractor (tba). Buchans Lanscaping withdrew their services in March 2024. A detailed map coloured map has been created to clarify areas of responsibility. London Lane & High Street cut back completed to enable improved regular maintenance. Regular monitoring of contractors to continue.
4 | Saxon Green | Ensure all equipment is maintained to standards required by ROSPA. | Parish Council | MEDIUM | ONGOING | 2024-04-01 |  | YES
RUNNING UPDATE: The last Annual ROSPA inspection indicated several issues which require attention. Further work required in relation to general maintenance.
5 | Footpaths and Roads | The Parish Council has no specific responsibility for footpaths and roads but undertakes to monitor areas of concern and raise such issues with relevant authorities including potholes and general repair. The Council will also help address concerns relating to footpaths and roads being obstructed by foliage from private land. | Parish Council | LOW | ONGOING | 2024-05-20 |  | YES
RUNNING UPDATE: London Lane: surface maintenance issues referred to CCC Highways via Clerk & Local Councillors. Update received in January. Scheme to be costed in new financial year.
6 | Flooding and drainage | The Parish Council has no specific responsibilities in relation to flooding and drainage other than on land owned by the Parish but undertakes to monitor areas of concern and raise such issues with relevant authorities. | Parish Council | LOW | ONGOING | 2024-05-20 |  | YES
RUNNING UPDATE: Areas of concern: CCC Highways scheme to resolve flooding at River Lane, debris in ditch at Saxon Green causing blockages in underground pipe. Flooding from drains on High Street referred to CCC Highways (Dec 2023).
7 | Communication with Parish | The Parish Council will communicate with the village in general via Facebook, 'Paxton Post', email list, website and notice boards. Parish Council meetings are open to all. Minutes and agendas are published. | Parish Council | LOW | ONGOING | 2025-01-01 |  | NO
RUNNING UPDATE: Next review of 'Paxton Post' - January 2025. Notice Boards in need of TLC.See Item No 21.
8 | Development and Planning | The Parish Council will express opinions on all planning applications within the Parish. Councillors will communicate and discuss such applications for a coordinated response to HDC. Notifications of planning applications will be shared on Facebook. Applications for larger or contentious developments will be included as agenda items in open Parish Council meetings for public consultation. | Parish Council | LOW | Ongoing | 2024-05-20 |  | NO
RUNNING UPDATE:
9 | Tree Survey | The Parish Council has a responsibility for the maintenance of trees on Parish Council land. A tree survey is carried out every two years by a qualified contractor who will recommend action to be taken to maintain the health and safety of trees. The Parish Council is not responsible for trees on land not owned by the Council but will contact the relevant authority or individual where tree growth affects public footpaths, roadways or land. | Parish Council | LOW | Survey bi annual | 2026-01-01 |  | NO
RUNNING UPDATE: Two dead trees on High Street referred to CCC Highways. Dead tree on London Lane referred to landowner.
10 | Traffic and Speeding | The Parish Council has undertaken to monitor and resolve traffic problems within the Parish. Reduction in speed limits at the southern end of the village have been implemented and an MVAS unit has been purchased and installed. A speedwatch group is active within the village | Parish Council | LOW | ONGOING | 2024-07-01 |  | YES
RUNNING UPDATE: Application for 20 MPH zones in Village resbmitted to CCC. LHI Application 2025/26 submitted to CCC. Await outcomes. Preparation for next LHI Application to start in July 2024 with early meeting with County Projects Officers. Discussion proposed at Annual Parish Meeting.
11 | Awarding grants | The Parish Council will consider making grants to organisations which are deemed to benefit the village. Applications for grants of larger amounts will need to comply with the PC grant strategy document. | Parish Council | MEDIUM | ANNUAL | 2024-05-01 |  | YES
Invite applications for May meeting and thereafter in the Autumn in line with new Grants Strategy.
12 | Precept | The precept is the portion of the Council Tax which the Council is able to set locally. The current precept is now £28,000. | Parish Council | LOW | ANNUAL | 2024-11-01 |  | NO
RUNNING UPDATE: Agreed £28,000 precept in 2024/25.
13 | Biodiversity in Great Paxton | Resident interest in biodiversity schemes, preservation of wild flowers and "No Mow May" campaign. The Parish Council will help and support any reasonable initiative to promote biodiversity etc within the village. | Parish Council | LOW | ONGOING | 2024-05-20 |  | YES
RUNNING UPDATE: Community Grant (Biodiversity) application unsuccessful. Need consolidated application for next round of funding. The PC will identify areas which should be allowed to grow wild without causing hindrance to footpaths and roadways. Areas identified on Mount Pleasant & Church Lane Green for protection of wild orchids. Reiterate this message to Grounds Maintenance Contractor.
14 | CIL funding | The Community Infrastructure Levy is a fund which allows the Parish Council to request assistance from the District Council for projects within the Parish. The likelihood of a positive CIL application is enhanced by a significant portion of the funding being provided by the Parish Council. | Parish Council | MED/HIGH | ANNUAL | 2024-10-01 |  | YES
RUNNING UPDATE: Awaiting notification of next round of funding. To be eligible, must be progressing potential scheme. Early consideration of potential project required.
15 | LHI funding | The Local Highways Improvements Fund allows the Parish Council to request assistance from the County Council for highways projects within the Parish. | Parish Council | MEDIUM | 2024-06-01 | Autumn 2024 |  | YES
RUNNING UPDATE: Application submitted for next round of LHI funding to include additional MVAS unit, solar panels & VAS Unit. Outcome expected June 2024. See Item No 10.
16 | Paxton Post | The Paxton Post is seen as an important part of village life, community and communication. It is funded by the Parish Council and revenue from advertising. | Parish Council | MEDIUM | ANNUAL | 2024-11-01 |  | YES
RUNNING UPDATE: Funding of the Paxton Post agreed for 2024/5. See Item No 7. Resignation of Editor prompts reconsideration of future at Annual Parish Meeting.
17 | Asset register | The Parish Council is required to maintain an up to date register of all owned assets. | Parish Council | NIL | ANNUAL | 2024-05-01 |  | YES
RUNNING UPDATE: The register should be reviewed and incorporated in website.
18 | Repairs to waste bin at Spinney | The waste bin is corroded and requires repair. | Councillors | LOW | none | 2024-04-01 |  | YES
RUNNING UPDATE:
19 | Move waste bin on Saxon Green away from play area | The waste bin is too close to the play area and would benefit from being moved across the path. | Councillors | LOW | none | 2024-04-01 |  | YES
RUNNING UPDATE:
20 | Seating on Village Green requires renovation | The seating is tired and requires cleaning and restaining. | Parish Council | LOW | 2024-04-01 | 2024-04-01 |  | YES
RUNNING UPDATE:
21 | Notice Board | Parish Council Notice Board (outside school) to be | Parish Council | LOW | 2024-05-20 | 2024-05-20 |  | YES
refurbished.
RUNNING UPDATE: